## Лист1
WORK PLAN Project 101126755 — GREENKG
|  |  |  | YEAR 1 01.11. 2023 - 31.10.2024 | [11 empty] | YEAR 2 01.11. 2024 - 31.10.2025 | [11 empty] | YEAR 3 01.11. 2025 - 31.10.2026
|  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
WP | Work Package/Task | Milestones | Deliverables/Months | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | Lead Beneficiary/ Due date | Type/ Dissemin Level
WP1 | Preparation: Building local expertise |  | M1-M15 | bar: Q1 M1 to Q1 M15
T 1.1 | Comparative state-of-the-art analysis and development of an Inventory of PC universities' needs in Green Dimensions | MS 1. Analysis of needs and gaps given in the Inventory | D1.1. Report on the needs and gaps analysis | [36 empty] | VU / M3 - January 31, 2024 | R - Document, Report/ PU | bar: Q1 M1 to Q1 M3; Q4 M36
T 1.2 | Preparation and approval of the training program for university administrators, teachers and IT specialists | MS 2. The training program is designed based on needs analysis | D1.2 Training program on GDU transformation | [36 empty] | VU / M4 - March 31, 2024 | R - Document, Report/ PU | bar: Q1 M2 to Q2 M5; Q4 M36
T 1.3 | Conducting a series of webinars | MS 3. A set of online webinars is conducted | [37 empty] | VU, HAW/ M7 - May 31, 2024 | bar: Q2 M4 to Q3 M7
T 1.4 | Organisation of ToT workshops in KG with a focus on the horizontal analysis of curricula and processes in Green Dimensions | MS 4. Training of Trainers workshops are conducted | [37 empty] | VU, HAW/ M9 - July 31, 2024 | bar: Q2 M4 to Q3 M9
T 1.5 | Preparation and organization of study tours to EU partners with a focus on EU practice in Digitalization & Green Policy | MS 5. Study tours to HAW and VU are organized | D1.3 Trained trainers in GDU transformation | [36 empty] | VU, HAW/ M12 - October 31, 2024 | Other/ PU | bar: Q2 M6 to Q4 M12; Q4 M36
T 1.6 | Conduct of second-wave training seminars for the staff of KG partner universities | MS 6. Second-wave training seminars conducted at KG partner universities | [37 empty] | VU, AKSU/ M15 - January 31, 2025 | bar: Q4 M11 to Q1 M15
WP2 | Development: GDU Model |  | M9-M24 | bar: Q3 M9 to Q4 M24
T 2.1 | Development of a GDU model | [38 empty] | KSTU M15 - January 31, 2025 | bar: Q3 M9 to Q4 M10
T 2.2 | Development of a GDU roadmap | MS 8. Adoption of the GDU roadmap | [37 empty] | KSTU/ M9 - July 31, 2024 | bar: Q3 M9 to Q4 M10
T 2.3 | Development of GDU internal regulation for submission to KG MES | MS 7. GDU transformation regulation developed for the Government approvement | D2.1 Approved GDU transformation regulation by MES KG | [36 empty] | KSTU, DAMFA, MES M15 - January 31, 2025 | R - Document, Report/ PU | bar: Q4 M10 to Q1 M15; Q4 M36
T 2.4 | Creation of GD Offices at KG partner universities | MS 9. Creation of GD offices at 10 KG partner universities | D2.2 Establishment of 10 GD Offices in HEIs of the Kyrgyz Republic | [36 empty] | DAMFA/ M9 - July 31, 2024 M12 - October 31, 2024 | R - Document, Report/ PU | bar: Q3 M9 to Q4 M12; Q4 M36
T 2.5 | Purchase and installation of equipment | bar: Q3 M9 to Q4 M12
T 2.6 | Development and approval of mandatory course on Green dimensions | MS 10. Development of a mandatory interdisciplinary course | D2.3 Adopted mandatory interdisciplinary module and elective microcredential module available at each KG partner university | [36 empty] | KSTU, HAW, MES, DAMFA, AKSU/ M24 - October 31, 2025 | R - Document, Report/ PU | bar: Q3 M9 to Q4 M24
T 2.7 | Horizontal analysis of existing curricula and syllabi. Development, peer-review and institutional adoption of one elective locally tailored microcredential module per each KG partner university | MS 11. Development of an elective microcredential modules | [37 empty] | HAW/ M24 - October 31, 2025 | bar: Q3 M9 to Q4 M24; Q4 M36
T 2.8 | Development of teaching/learning materials adopted to b-learning | bar: Q4 M10 to Q4 M24
WP3 | Quality Assurance |  | M2-M36 | bar: Q1 M2 to Q1 M27
T 3.1 | The establishment of QA group of the project | MS 12. The project QA group is established | [37 empty] | IHSM/ M24 - October 31, 2025 | bar: Q1 M2 to Q4 M24
T 3.2 | Development of the project Quality Assurance plan | MS 13. The project QA Plan is developed and approved | [37 empty] | IHSM/ M24 - October 31, 2025 | bar: Q1 M2 to Q4 M24
T 3.3 | Training on QA | [38 empty] | IHSM | bar: Q1 M3 to Q2 M4; Q4 M10 to Q4 M12
T 3.4 | Establishment of the project self-monitoring system | MS 14. QA framework and review methodology for project developments is implemented and the project self- monitoring system is established | D3.1 QA framework & review methodology for project activities and developments, self-monitoring system for project developments | [36 empty] | IHSM/ M4 - February 29, 2024 M5 - March 31, 2024 | DMP - Data Management Plan/ SEN | bar: Q1 M2 to Q2 M5; Q4 M36
T 3.5 | Project QA evaluation |  | D3.2 Interim QA report. | [36 empty] | IHSM/ M18 - April 30, 2025 | R - Document, Report/ SEN | bar: Q2 M5 to Q3 M9; Q1 M14 to Q2 M18; Q4 M36
|  |  | D3.3 Final QA report | [36 empty] | IHSM/ M33 - July 31, 2026 | R - Document, Report/ SEN | bar: Q3 M19 to Q4 M23; Q2 M28 to Q3 M33; Q4 M36
| External evaluation | MS 15. External evaluation is done | [37 empty] | IHSM/ M36 - October 31, 2026 | bar: Q3 M33 to Q4 M36
WP4 | Exploitation: Implementation & Networking |  | M16-M36 | bar: Q2 M16 to Q4 M36
T 4.1 | Implementation of components of GDU model. Digitalization of administrative, educational processes at target universities | MS 16. Pilot GDU model is started to implemented at target universities | [37 empty] | OSU/ M16 - February 29, 2025 | bar: Q2 M16 to Q4 M36
T 4.2 | Pilot & Delivery of mandatory course and elective modules on Green Dimensions | MS 17. Pilot & Delivery of mandatory course and elective modules on Green Dimensions | D4.1 Launched new online mandatory course on Green dimension with e- materials at KG universities | [36 empty] | OSU/ M24 - October 31, 2025 | R - Document, Report/ PU | bar: Q2 M16 to Q4 M24; Q4 M36
T 4.3 | Creation of the National GDU Network’s forum on the project website | MS 18. The GDU Network is established | D4.2 National GDU Network established | [36 empty] | OSU/ M20 - June 30, 2025 | Other/PU | bar: Q2 M16 to Q3 M20; Q4 M36
T 4.4 | Development of the GDU Network’s Plan | MS 19. Development of the Network’s Plan | D4.3 The GDU Network’s Plan | [36 empty] | OSU, DAFMA, BEN/ M20 - June 30, 2025 | DMP - Data Management Plan/ SEN | bar: Q2 M16 to Q3 M20; Q4 M36
WP5 | Dissemination |  | M3-M36
T 5.1 | Development of Dissemination and Communication Plan | MS 20. Delivery of Dissemination and Communication plan | D5.1 Dissemination & Communication plan | [36 empty] | KSTU/ M3 - January 31, 2024 | DMP - Data Management Plan/ SEN | bar: Q1 M3; Q4 M36
T 5.2 | Development of the project website and Networking Forum | MS 21. Development and launch of the project website | D5.2 Project website | [36 empty] | KSTU/ M6 - April 30, 2024 | DEC - Websites, patent filings, videos, etc./PU | bar: Q1 M3 to Q2 M6; Q4 M36
T 5.3 | Organisation and conduct of 3 national workshops | MS 22. Organization and conduct of 3 international conferences | [37 empty] | KSTU/ M18 - April 30, 2025 | bar: Q2 M16 to Q3 M19; Q4 M24 to Q2 M28
T 5.4 | Preparation of news of the project outputs for mass media | bar: Q3 M7 to Q4 M36
T 5.5 | Presentation of the Project at local and international events | bar: Q3 M9 to Q4 M36
T 5.6 | Organisation and conduct of the final project congress in Bishkek | MS 23. Final project dissemination event | D5.3 The project final dissemination event | [36 empty] | KSTU/ M33 - July 31, 2026 | Other/ PU | bar: Q3 M31 to Q3 M33; Q4 M36
|  |  | D5.4 A report on the implementation of the Dissemination plan at mid-term | [36 empty] | DAMFA, KSTU/ M18 - April 30, 2025 | R - Document, Report/ PU | bar: Q2 M16 to Q2 M18
|  |  | D5.5 A report on the implementation of the Dissemination plan at the end of the project | [36 empty] | DAMFA, KSTU/ M36 - October 31, 2026 | R - Document, Report/ PU | bar: Q4 M34 to Q4 M36
WP6 | Project Management |  | M1-M36
T 6.1 | Update of the project Work Plan |  | D6.1 The project Work Plan | [36 empty] | DAMFA/ M2 -December 31, 2023 | R - Document, Report/ SEN | bar: Q1 M1 to Q1 M2; Q4 M36
T 6.2 | Kick-off meeting, elaboration of partnership agreements, establishment of the project management board and steering group | MS 24. The project kick-off meeting | D6.2 Kick-off meeting | [36 empty] | DAMFA/ M3 - January 31, 2024 | Other/SEN | bar: Q1 M2 to Q1 M3; Q4 M36
T 6.3 | Development of the project Sustainability Plan | MS 26. Delivery of Sustainability plan | 6.3 Project Sustainability Strategic Plan | [36 empty] | DAMFA/ M5 - March 31, 2024, M2-M36 - December 12, 2023 - October 31, 2026 | R - Document, Report/ PU | bar: Q1 M2 to Q4 M36
T 6.4 | Signing the project partnership agreements | MS 25. Partnership agreements signed | [37 empty] | DAMFA, BEN/ M6 - April 30, 2024 | bar: Q2 M4 to Q2 M6
T 6.5 | Conducting regular project coordination meetings
T 6.6 | Control and monitoring delivery of the project activities according timeline
T 6.7 | Identifying, preventing and monitoring risks in the project life
T 6.8 | Conflict management
T 6.9 | Preparation of mid-term and final reports. Reporting | MS 27. Midterm financial statement and technical report MS 28. Final financial statement and technical report | D6.4 Progress Report | [36 empty] | DAMFA, BEN/ M18 - April 30, 2025 M36 - October 31, 2026 | R - Document, Report/ SEN | bar: Q2 M17 to Q3 M20; Q3 M33 to Q4 M36
Note:
Durtion of Work packages - Months
Due date of Deliverables
Due date of Milestones
Implementation of WP Tasks
2023
2024
2025
2026